## Read-me
Assessment Workplan Template
Purpose
The assessment workplan is a document that summarises the key steps of the assessment exercise, estimated timeframes for completion, and focal points for each described task.
Adapting the assessment workplan template
The assessment workplan is a flexible template designed to assist in planning an assessment exercise. It outlines the phases of the assessment and provides details about the associated outputs, activities, and main tasks. The template can be customized to suit the specific needs of the operation. For more comprehensive planning, additional tasks can be added to each activity, or more activities can be included for each phase. The template includes two columns for assigning a focal point responsible for each activity and the main colleagues who will support the task. Key Points to Consider: 1. Set Realistic Deadlines: Ensure that the work plan establishes achievable deadlines for each phase and task. 2. Expect the Unexpected: Keep in mind that unexpected events may occur during the exercise, so build flexibility into the plan. 3. Collaboration is Essential: Always develop the work plan in close collaboration with the partners involved in the assessment exercise. Customization Guidelines: 1. Review the template and tailor it to match the specific requirements of your assessment exercise. 2. Add or remove phases, activities, or tasks as needed. 3. Assign responsible focal points and supporting colleagues to each activity. 4. Set realistic deadlines for the completion of each task, considering potential contingencies. The purpose of this template is to serve as a helpful guide, so feel free to adapt it according to your assessment exercise's unique characteristics and scope.
For more information, please visit the UNHCR Assessment and Monitoring Resource Centre
Assessment and Monitoring Resource Centre

## Assessment Workplan Template
Assessment Workplan Template
Please note: The timeframe and tasks should be adjusted according to the exercise
Phase | Outputs | Activities | Tasks | Lead person | Support person(s) | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  | Jul
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Understand context | Assessment Concept Note | Evaluate data needs | Define scope and scale of the crisis and context
Identify initial information needs
|  | Outreach to stakeholders and discussions to initiate collaboration | Engage key stakeholders, possible partners and community members on potential assessment objectives
|  | Document decisions and plans with stakeholders | Evaluate if further assessments are needed
Draft the assessement concept note
Plan the assessment | Part I of assessment methodology and data analysis plan | Set the objectives and establish coordination arrangements | Define the assessment objectives
Agree and define coordination arrangements, including possible MoU
|  | Define information needs | Select the analytical framework according to agreed objectives
Detail the information needs within the analytical framework, adjusting according to the agreed objectives
Draft Part I of the assessment methodology
Draft the data analysis plan
Collate and collect data | Secondary data review analysis plan and report | Secondary data review | Plan the secondary data review
Collect and collate the data
Jointly analyse and identify information gaps.
Complete secondary data review report and share conclusions
| Assessment methodology, analysis plan, data collection tools, and primary data collected | Primary data collection | Define primary data collection methods
Define the sampling approach
Complete the methodology document
Complete the data analysis plan
Develop primary data collection tools and incorporate revisions
Prepare tool in KoBo
Prepare enumerator instructions and training package
Train the data collection team
Pilot primary data collection tools and incorporate revisions
Define logistical arrangements
Collect field data and supervise data collection
Draw conclusions | Analysis and initial findings | Analysis | Conduct data cleaning
Conduct data analysis
Interpret the data through joint analysis with key stakeholders and partners
Revise preliminary findings based on feedback from key stakeholders and partners
Develop recommendations with key partners
Share information | Recommendations, report(s) and other information products | Assessment report | Draft preliminary report and share for feedback/ endorsement
Draft final report and executive brief
|  | Other produts | Develop additional products (e.g. PowerBI dashboard, map)
|  | Dissemination | Develop dissemination plan
Conduct dissemination
Assessment and Monitoring Resource Centre