## Guidance
PROJECT PERFORMANCE VERIFICATION - PMC02
Note: Questions with * are mandatory.
1. PRELIMINARY INFORMATION
Q # | Question/Field Title | Response Type | Supporting Documents / References | Responsibility | Guidance
1 | Implementer* | Free text | Cloud ERP | UNHCR | Copy and paste the name from Cloud ERP to ensure accuracy.
2 | Partner Agreement / Contract* | Free text | Cloud ERP | UNHCR | Copy and paste the name from Cloud ERP to ensure accuracy.
3 | Verification Period Start Date | Calendar | Previous PMC02, if any | UNHCR | For the first PMC02, the start date should be the project start date. For each subsequent PMC02, the start date should be one day after the end date of the previous PMC02.
4 | Verification Period End Date | Calendar |  | UNHCR | Enter the date on which the current performance verification (PMC02) is initiated. This date represents the end of the verification period.
TOPIC | 2. STATUS OF IMPLEMENTATION MONITORING RECOMMENDATIONS (THIS INCLUDES IMPLEMENTATION MONITORING FIELD ISSUES, AMONG OTHERS)
5 | Summarize all performance‑related issues or recommendations identified during monitoring of this partner’s implementation within the verification period. | Free text | Field issue reports, field monitoring reports, community feedback, and/or other reports relevant to project implementation. | UNHCR | Summarize the key performance-related issues, challenges, observations, and recommendations identified during the verification period based on continuous monitoring and supporting documentation. Reflect findings and recommendations raised by both UNHCR and the partner, where applicable. Focus on significant matters affecting implementation, delivery of results, compliance, quality, timeliness, or other aspects of performance, and provide a balanced and factual overview.
6 | Partner's feedback on delays in closing recommendations. | Free text |  | Partner | Complete this section if there are delays in closing recommendations. Summarize the reasons for the delay, including any challenges, constraints, or circumstances affecting timely closure. The response should be factual, concise, and supported by available evidence where applicable.
7 | UNHCR's feedback on delays in closing recommendations. | Free text |  | UNHCR | Complete this section if there are delays in closing recommendations. Summarize the reasons for the delay, including any challenges, constraints, or circumstances affecting timely closure. The response should be factual, concise, and supported by available evidence where applicable
TOPIC | 3. PROGRESS ON RESULTS
Q #
8 | By outcome statement, is implementation proceeding as planned towards indicator targets? Attach evidence of partner’s reported actuals against planned output indicators. | Yes / No | Partner's progress report on results. | UNHCR | Consider whether the evidence provided demonstrates that implementation is on track to achieve the planned output indicator targets for the verification period. Select 'Yes' if implementation is proceeding as planned; otherwise, select 'No.'
9 | Record the latest reported progress against each planned indicator as a percentage (calculated as the latest reported actual value divided by the total target, where applicable). | Free text | Partner's progress report on results. | UNHCR | Capture the most recent reported status of achievement against the planned indicator targets, including the latest achieved value and the corresponding percentage of progress. The percentage should be calculated by dividing the latest achieved value by the target value and multiplying the result by 100. Where a percentage cannot be calculated, provide the latest reported value and a brief explanation. Ensure that all figures are based on the most recent available data and are supported by relevant evidence.
10 | If implementation is not proceeding as planned, describe the challenges encountered and how they affected progress? | Free text |  | Partner | Complete this section if the response to question 8 is 'No.' Briefly describe the challenges, delays, or other factors affecting implementation, their impact on planned results, the reasons for any underperformance, and any corrective measures being taken. Include supporting evidence where available.
TOPIC | 4. STRENGTHENED PSEA MEASURES
Q #
11 | Progress on PSEA Capacity Strengthening Implementation Plan. | Dropdown list | PSEA status report from PowerBI | UNHCR | Select the status that best reflects progress in implementing the PSEA Capacity Strengthening Implementation Plan (CSIP) during the verification period: N/A (if "Full capacity" status or Government partner) In Progress Overdue Not Started
12 | If the CSIP status is overdue or not started, explain briefly the reason for the delay. | Free text |  | Partner | Complete this section if the response to question 11 is "Overdue" or "Not Started." Provide a brief explanation of the reasons for the delay, including any key factors preventing progress as planned.
TOPIC | 5. PARTNER'S REPORT
Q #
13 | Partner's brief narrative on project's progress and/or challenges. | Free text |  | Partner | Provide a concise summary of the project's progress, highlighting key achievements, challenges, delays, risks, trends, or other factors affecting implementation and the achievement of planned results.
14 | UNHCR's brief narrative on project's progress and/or challenges. | Free text |  | UNHCR | Provide a concise summary of the project's progress, highlighting key achievements, challenges, delays, risks, trends, or other factors affecting implementation and the achievement of planned results.
TOPIC | 6. OPERATIONAL CHALLENGES AND CORRECTIVE ACTIONS
Q #
15 | Are there any recommended project adjustments or corrective actions? | Yes / No | All supporting documents reviewed during the performance verification. | Drafted by UNHCR; Reviewed/Completed by Partner | Consider whether the evidence available during the verification period, including monitoring findings and discussions with the partner, indicates a need for project adjustments or corrective actions. Select 'Yes' if any adjustments or corrective actions are warranted; otherwise, select 'No.'
16 | Recommended project adjustments or corrective actions. | Free text |  | Drafted by UNHCR; Reviewed/Completed by Partner | Complete this section if the response to question 15 is 'Yes.' Describe the proposed actions and the reason for each recommendation. Clearly explain how the proposed measures will address the identified issue, improve implementation, mitigate risks, or support the achievement of planned results. Reflect recommendations raised by both UNHCR and the partner, where applicable.
17 | Based on the current Risk Register, performance, and operational challenges, have any risk levels increased, or have any additional risks been identified? | Yes / No | Monitoring reports, field issues report, partner's reports, and/or partner's UNHCR/partner responses to questions in the current performance verification. | Drafted by UNHCR; Reviewed/Completed by Partner | Consider whether the evidence available during the verification period indicates that the Risk Register should be reviewed due to increased existing risks or newly identified risks. Select 'Yes' if a review is required; otherwise, select 'No.'
18 | If above answer is 'Yes,' indicate the increased or newly identified risks requiring Risk Register review. | Free text |  | Drafted by UNHCR; Reviewed/Completed by Partner | Complete this section if the response to question 17 is 'Yes.' Briefly describe the risk, its potential impact on the project, and any proposed or ongoing mitigation measures. Where applicable, indicate whether the risk should be added to or updated in the Risk Register.
Q # | PREPARED AND SIGNED BY UNHCR
19 | Name, Title | Free text |  | UNHCR | UNHCR to enter the preparer's name and title.
20 | Signature | Free text |  | UNHCR | UNHCR to sign.
TOPIC | PREPARED AND SIGNED BY PARTNER
21 | Partner Acceptance Status | Dropdown list |  | Partner | Select the applicable acceptance status: Accepted, Accepted with Comments, or Not Accepted.
22 | Partner Notes | Free text |  | Partner | Add notes, as applicable.
23 | Name, Title | Free text |  | Partner | Partner to enter the preparer's name and title.
24 | Signature | Free text |  | Partner | Partner to sign.

## Example
PROJECT PERFORMANCE VERIFICATION - PMC02
Note: Questions with * are mandatory.
1. PRELIMINARY INFORMATION
Q # | Question/Field Title | Response Type | Supporting Documents / References | Responsibility | Response | Suggested Field Issues to be Raised
1 | Implementer* | Free text | Cloud ERP | UNHCR | People in Need Slovakia
2 | Partner Agreement / Contract* | Free text | Cloud ERP | UNHCR | 23162Y26M203029
3 | Verification Period Start Date | Calendar | Previous PMC02, if any | UNHCR | 2026-01-01
4 | Verification Period End Date | Calendar |  | UNHCR | 2026-04-15
TOPIC | 2. STATUS OF IMPLEMENTATION MONITORING RECOMMENDATIONS (THIS INCLUDES IMPLEMENTATION MONITORING FIELD ISSUES, AMONG OTHERS)
5 | Summarize all performance‑related issues or recommendations identified during monitoring of this partner’s implementation within the verification period. | Free text | Field issue reports, field monitoring reports, community feedback, and/or other reports relevant to project implementation. | UNHCR | Monitoring activities confirmed that project implementation is progressing overall in line with the project workplan. Strong performance was observed in Sport for Protection activities and awareness-raising sessions. Challenges identified included slower progress in community events and volunteer activities, uneven implementation across some locations, communication gaps regarding activity schedules, and lower refugee participation in certain activities. Recommendations included strengthening outreach, improving communication with beneficiaries, and increasing focus on underperforming outputs. | UNHCR to raise a Field Issue (Recommendation) for Partner follow-up: Increase refugee participation in community events, counselling services, and information sessions through targeted outreach campaigns, strengthened referral pathways, and regular monitoring of participation rates in underperforming locations.
6 | Partner's feedback on delays in closing recommendations. | Free text |  | Partner | One recommendation related to expanding outreach activities in underserved locations remains open. The delay was due to limited staff capacity during the reporting period. The partner has initiated the required actions and expects to close the recommendation during the next quarter.
7 | UNHCR's feedback on delays in closing recommendations. | Free text |  | UNHCR | N/A – No delays in closing recommendations were identified during the verification period.
TOPIC | 3. PROGRESS ON RESULTS
Q #
8 | By outcome statement, is implementation proceeding as planned towards indicator targets? Attach evidence of partner’s reported actuals against planned output indicators. | Yes / No | Partner's progress report on results. | UNHCR | Yes | UNHCR to raise a Field Issue (Appreciation) for Partner: Sport for Protection activities significantly exceeded planned targets and successfully promoted participation, inclusion, and interaction between refugee and host community children across multiple locations.
9 | Record the latest reported progress against each planned indicator as a percentage (calculated as the latest reported actual value divided by the total target, where applicable). | Free text | Partner's progress report on results. | UNHCR | • Sport for Protection participants: 556/169 (329%) • Participants in tournaments and sports events: 639/800 (80%) • Children participating in awareness sessions: 820/169 (485%) • Children and caregivers receiving child protection services: 259/1,000 (26%) • Participation in community events and volunteer activities: 402/600 (67%) • Advocacy interventions: 4/10 (40%) • Individuals receiving information on services and rights: 593/2,000 (30%) • Counselling sessions delivered: 167/600 (28%) Overall, implementation is progressing towards planned results. Sport for Protection activities and awareness-raising sessions have exceeded targets, while child protection services, counselling sessions, advocacy interventions, and information provision require accelerated implementation to achieve annual targets.
10 | If implementation is not proceeding as planned, describe the challenges encountered and how they affected progress? | Free text |  | Partner | N/A.
TOPIC | 4. STRENGTHENED PSEA MEASURES
Q #
11 | Progress on PSEA Capacity Strengthening Implementation Plan. | Dropdown list | PSEA status report from PowerBI | UNHCR | Overdue
12 | If the CSIP status is overdue or not started, explain briefly the reason for the delay. | Free text |  | Partner | Implementation of several activities under the PSEA Capacity Strengthening Implementation Plan has been delayed due to staff turnover in key PSEA focal point functions and the resulting need to reassign responsibilities and complete training for newly hired personnel. The partner has reviewed the outstanding activities and proposed a revised implementation timeline, including a request to extend the CSIP implementation period by three months. Completion of the remaining activities is expected during the next quarter.
TOPIC | 5. PARTNER'S REPORT
Q #
13 | Partner's brief narrative on project's progress and/or challenges. | Free text |  | Partner | During the verification period, the project continued to deliver planned community-based protection and integration activities across the targeted locations. Strong participation was recorded in Sport for Protection activities and awareness-raising sessions, demonstrating continued interest from both refugee and host communities. Challenges included uneven participation across locations, lower-than-expected uptake of some counselling and community activities, and the need to strengthen outreach to refugees in selected areas. The partner is taking steps to increase community engagement and improve access to services during the next implementation period. | Partner to raise a Field Issue (Recommendation) for UNHCR follow-up: Continue regular coordination and implementation support meetings to facilitate timely resolution of operational challenges and implementation bottlenecks.
14 | UNHCR's brief narrative on project's progress and/or challenges. | Free text |  | UNHCR | UNHCR observed satisfactory implementation progress during the verification period, with several indicators showing strong achievement against planned targets. Partnerships with schools, municipalities, and community stakeholders contributed positively to project delivery. While overall implementation remains on track, additional attention is required to improve performance under community engagement, counselling, and information provision activities. UNHCR encourages continued efforts to strengthen outreach, ensure balanced delivery across locations, and enhance linkages between protection, counselling, and community-based interventions.
TOPIC | 6. OPERATIONAL CHALLENGES AND CORRECTIVE ACTIONS
Q #
15 | Are there any recommended project adjustments or corrective actions? | Yes / No | All supporting documents reviewed during the performance verification. | Drafted by UNHCR; Reviewed/Completed by Partner | Yes
16 | Recommended project adjustments or corrective actions. | Free text |  | Drafted by UNHCR; Reviewed/Completed by Partner | Review the implementation approach to strengthen underperforming community engagement and counselling activities. The partner and UNHCR should assess whether additional outreach activities or a reallocation of efforts across activities are required to improve achievement of the related indicators. If progress remains below expectations during the next month, a project workplan amendment may be considered. | UNHCR to raise a Field Issue (Recommendation) for Partner follow-up: Develop and implement an action plan to improve performance under counselling, information provision, and community engagement indicators, including clear targets, timelines, and responsibilities.
17 | Based on the current Risk Register, performance, and operational challenges, have any risk levels increased, or have any additional risks been identified? | Yes / No | Monitoring reports, field issues report, partner's reports, and/or partner's UNHCR/partner responses to questions in the current performance verification. | Drafted by UNHCR; Reviewed/Completed by Partner | Yes
18 | If above answer is 'Yes,' indicate the increased or newly identified risks requiring Risk Register review. | Free text |  | Drafted by UNHCR; Reviewed/Completed by Partner | Risk ID2 (Project activities not met) requires review due to slower progress under some indicators and uneven implementation across locations. A new risk related to communication and beneficiary awareness was identified following community feedback, which may affect participation and access to services. Continued monitoring and mitigation measures are recommended.
Q # | PREPARED AND SIGNED BY UNHCR
19 | Name, Title | Free text |  | UNHCR | XXXXXXXXXX, XXXXXXXXXX
20 | Signature | Free text |  | UNHCR
TOPIC | PREPARED AND SIGNED BY PARTNER
21 | Partner Acceptance Status | Dropdown list |  | Partner | Accepted
22 | Partner Notes | Free text |  | Partner | The partner agrees with the findings and recommendations and will continue efforts to improve outreach, communication, and implementation coverage.
23 | Name, Title | Free text |  | Partner | XXXXXXXXXX, XXXXXXXXXX
24 | Signature | Free text |  | Partner

## Changes required (hidden)
The project field name should have 20 or less characters
For dropdown lists, after selecting an option, the Commect box will not be available. Users may enter any additional comments in the comment box below. We will display the note: "Please add your comments in the comment box below."