## Sheet1
WASH KAP MDC Deployment Checklist
Project phase | Task | Approx. time* | How long before the data collection you should start thinking about it | Further note / warning | checkbox
General planning phase | Plan the overall budget for your WASH KAP to ensure that you have the budget line | 0.5 days | The year before, when you need to work on your budgets | Refer to the budget template on http://wash.unhcr.org/download/wash-kap-survey-module-0-general/
General planning phase | Familiarize yourself with the documentation available on the WASH monitoring system website, such as the 2 pagers available, the key indicators, the global form and the manuals for each phase: http://wash.unhcr.org/wash-monitoring-system | 1 day | 3 months
General planning phase | Take previous recommendations into account: If a WASH KAP was already conducted in the year(s) before, check their conclusions and recommendations for the new WASH KAP | 0.5 days | 3 months
General planning phase | Assess the context: is it safe in terms of security (and allowed) to walk in the camps with mobile devices? Is it safe running a survey at the moment? Are there questions that might need to be removed for a specific ethical or practical reason? What is the feedback from other agencies who already implemented similar surveys in the past months ? | 0.5-3 days | 3 months
General planning phase | Define the sampling strategy to determine the number of enumerators / team leaders needed and the number of days for data collection | 0.5-1 days | 2 months | Based on the material available here http://wash.unhcr.org/download/wash-kap-survey-module-0-general/
General planning phase | Plan the KAP time frame and inform relevant stakeholders: the period for setting up the methodology, workshop to define a customised version of the form, translation of the form, technical adaptation of the form to mobile format, scheduling trainings for team leaders and enumerator, define a pilot site, data collection, analysis and reporting | 0.5 days | 2 months
General planning phase | Plan the human resources: the WASH expert who will coordinate the whole deployment, the stakeholders to involve in the design of the form and methdology (such as implementing partners, other WASH actors...), the IM tech proficient person who will set up the system and adapt the mobile form, the translator who will translate the form into the local language, the team leaders who will coordinate a small team of enumerators, the enumerators themselves ... | 0.5-2 days | 2 months | Strong recommendation to have an IM person on board during the whole process to ensure that there are no technical issues during the deployment. Note that water collection is usually a gender sensitive topic and having women on the enumerator team can vastly facilitate/improve the quality of results by increasing the confidence of women when responding (example: the menstrual hygiene module). However in some contexts, women can't walk safely in camps and in that case mixed teams of both male and female enumerators are advised.
General planning phase | Prepare the detailed budget based on the previous steps | 0.5 days | 2 months | Refer to the budget template on http://wash.unhcr.org/download/wash-kap-survey-module-0-general/ Keep in mind that if the enumerators or team leader do not have access to wifi every day, you may wish to subscribe to a data plan for them.
General planning phase | Check existing maps of the camp and decide if you want to benefit from mapping the camp on OpenStreetMap to visualise the WASH KAP indicators on an up-to-date map. If the camp has not been properly mapped yet, you can request remote mapping through volunteers coordinated by CartONG | 2 hours | 2 months | This will allow you to understand the results and improve your programming. You can check here: https://www.openstreetmap.org if the camp has been mapped Keep in mind that if the data isn't available or up to date, it could take a few weeks for the mapping to occur.
General planning phase | Choose and buy the hardware (one device per enumerator) if it is not already available, as well as the associated equipment: batteries, protection cases, neck straps, cables/chargers etc. | 0.5-2 days | 1 to 2 month | Keep in mind that your admin procedures could slow down the procurement or that phones could be stuck in customs if you wish to buy them from abroad. Check out http://blog.cartong.org/2017/04/27/choosing-mobile-device/ and http://blog.cartong.org/2018/01/18/mobile-data-collection-in-emergencies-which-phones-or-tablets-can-do-the-job/ for help choosing devices
Preparation phase | Recruit/on-board whoever is necessary in terms of HR | 0.5-2 days | 1 month | It is important to ensure that enumerators speak the local language well (more important than understanding the official language of the country), else you should plan to use translators.
Preparation phase | Pre-identify key elements in the questionnaire that need to be specified in the global form (type of water container, type of latrine...) and if needed plan focus group discussions before the KAP deployment to ensure your form is perfectly adapted to the current WASH context in the specific camps | 1-3 days | 1 to 1.5 month | It is highly advisable to take pictures of specific elements so that you can show the enumerators the different types of boreholes, latrines, water containers etc.
Preparation phase | Prepare and run a workshop with relevant stakeholders (Implemening Partners, other WASH actors...) to agree on the methdology and content of the customised version of the form (optional questions, required modifications to anything but the standard indicators...) | 1-2 days | 1 month
Preparation phase | Create a paper version of your adapted form (based on the global paper form) | 2-4 hours | 1 month
Preparation phase | Translate the paper form into the relevant local language of your adapted form | 1-2 days | 3 weeks | The translation of the form is a key step to ensure data quality
Preparation phase | Create an account on the UNHCR KoBo website (Kobo.unhcr.org) to manage data collection | 0-2 hours | 3 weeks | We usually advise to create more than one account, you will also need to plan for an account for the team leaders and each stakeholder who has access to the data to ensure maximum involvement (with read or modification rights as prefered).
Preparation phase | Adapt the global mobile form to your local context based on the agreed paper version. The time needed will depend on the number of changes required, the implementation of an extra language, as well as how used to adapting a mobile form you are. | 0.5-3 days | 3 to 2 weeks | Decide between coding directly in the XLSForms template, a widely used open source survey format, (and then importing it to Kobo) or importing and adapting directly in the Kobo platform. Advantages of the first: steeper learning curve but covers all possible types of modifications. It is also easier in the long term, if this is something you want to do regularly. Advantages of the second: More user-friendly but less flexible than XLSForm coding. If needed, ask CartONG for advice/validation.
Preparation phase | Test your form for data collection on one phone, and export a dataset to open it with the analysis tool to ensure that everything works as it should! | 2-4 hours | 3 to 2 weeks
Preparation phase | Plan relevant Standard Operating Procedures (SOPs) | 0-4 hours | 3 to 2 weeks | Consider how the data collection will work, how data will be synchronised at night, where smatphones will be charged, how survey stakeholders can access the data, the supervision mechanism (which should include, permanent contact – hotline, daily questionnaire review, random oversight of interviews by survey managers/team leaders, daily briefing and debriefing) etc.
Preparing and running the training & pilot | Adapt the generic training materials of enumerators to make the key notions understandable in the local context. | 1 day | 2 weeks | Integrate local terminology and pictures of latrines, water containers, water sources previously collected and agreed to ensure proper understanding by enumerators
Preparing and running the training & pilot | Prepare paper handouts of the form for the enumerators to properly understand each module during the training. | 2 hours | 2 weeks
Preparing and running the training & pilot | Install ODK Collect on the enumerators phones, adapt its settings to your needs and download the surveys through the KoBo server. | 1-4 hours | 1 week | Ensure that Kobo Collect is not also on the phones as both apps being installed at the same time creates technical issues! If ODK collect was already installed, clean it of previous forms and data and check the settings.
Preparing and running the training & pilot | Run the training sessions for the team leaders and enumerators (if necessary with a translator) | 1 to 3 days | 1 week | It is essential to focus on the key notions of the KAP form in detail to ensure proper understanding. Run test scenarios to ensure that all enumerators fill in the same information for the same case, but also interview techniques, ensuring that they fully understand the way they should behave and risk of bias, asking for consent, the sampling strategy, the use of the mobiles and ODK Collect, etc. Plan a specific session for team leaders to explain what you expect from them in terms of supervision
Preparing and running the training & pilot | Plan a full day of pilot field testing and debriefing | 1-2 days | 3 days | This is to ensure proper understanding of the notions, proper behaviour and data checks to ensure that everything is as it should be. It can require adding a short training on whatever has not been properly understood. The pilot should be as close to real-life situations as possible so that specific local situations that would need to be integrated in the form or discussed further with the enumerators can be tested.
Preparing and running the training & pilot | Prepare paper handouts or tips and tricks that may seem necessary on the content of the form or key aspects of the data collection (water collection paper form if necessary) based on the conclusion of the pilot. | 0-4 hours | 2 days
Preparing and running the training & pilot | Review form content after training / pilot testing and test it thoroughly on the phone | 0.5-1 day | 2 days
Preparing and running the training & pilot | Download the newer mobile version of the form to the phones | 0-3 hours | 1 day
Preparing and running the training & pilot | Distribute paper handouts of the form for the enumerators as back-ups, in case interviewees do not consent to the use of mobile phones or in case of a technical issue with a phone (battery, bug...) | 0.5 hour | 1 day
Preparing and running the training & pilot | Distribute handover-form of smartphones based on your logistics procedures | 0.5 hour | 1 day
You are now ready to collect the data :)
* Depending on the complexity of the context, and whether a KAP / mobile KAP / mobile KAP using the global tools has been used in the past or not.