## Sheet1
Roll Out Timeline
|  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11
| Activities / Days | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 50 | 51 | 52 | 53 | 54 | 55 | 56
Recruitement | bar: Week 1 1 to Week 1 5
Procurement | bar: Week 2 8 to Week 2 9
Training Tamuli Reg Team + Interpreter Cheraton | bar: Week 2 10 to Week 2 12
Training Roving Reg Team + Interpreter Bowtown | bar: Week 2 10 to Week 2 12
Roving Team | Information Campaign Lauperville | bar: Week 3 18 to Week 3 19
Registration Lauperville | bar: Week 4 22 to Week 4 26
Set up of registration site | bar: Week 3 15 to Week 3 17
Information Campaign Cheraton | bar: Week 3 15 to Week 3 16
Fixing Cheraton | bar: Week 3 17 to Week 3 18
Registration Cheraton | bar: Week 3 19; Week 4 22 to Week 4 25
Set up of registration site | bar: Week 3 15 to Week 3 17
Information Campaing Bowtown | bar: Week 3 15 to Week 3 19
Fixing Bowtown | bar: Week 4 22 to Week 4 26; Week 8 55
Regisration Bowtown | bar: Week 5 29 to Week 5 33; Week 6 36 to Week 6 41; Week 7 43 to Week 7 48; Week 8 50 to Week 8 55; Week 9 50 to Week 9 55; Week 10 50 to Week 10 55; Week 11 50 to Week 11 55
Jabal | Fixing | bar: Week 3 15 to Week 3 19; Week 4 22 to Week 4 26; Week 5 29 to Week 5 33; Week 6 36 to Week 6 40; Week 7 43 to Week 7 47; Week 8 55
Nasib | Fixing | bar: Week 3 15 to Week 3 19; Week 4 22 to Week 4 26; Week 5 29 to Week 5 33; Week 6 36 to Week 6 40; Week 7 43 to Week 7 47
Turner Town | Information Campaign | bar: Week 4 22 to Week 4 26
Fixing | bar: Week 5 29 to Week 5 33; Week 6 36 to Week 6 40; Week 7 43 to Week 7 45
Tamuli | Set up of registration site | bar: Week 3 15 to Week 3 17
Registration | bar: Week 3 18 to Week 3 19; Week 4 22 to Week 4 27; Week 5 29 to Week 5 34; Week 6 36 to Week 6 41; Week 7 43 to Week 7 48; Week 8 50 to Week 8 55; Week 9 50 to Week 9 55; Week 10 50 to Week 10 55