## ENGLISH example
| August | [12 empty] | September | [29 empty] | October
| 15-19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18-28
Finalization of survey protocol and budget | bar: August 15-19
Preparation of the interviewer guide, of the questionnaire and of all needed tools for the survey and training. | bar: August 15-19
Arrival of the UNHCR Consultant in country | bar: August 20
Validation of the sample size and cluster selection (first degree) | bar: August 21 to August 22
Finalization of the interviewer guide, of the questionnaire and of all needed tools for the survey and the training | bar: August 23 to August 25
Organization of the interviewers training (logisitic, printing, etc.) | bar: August 24 to August 25; August 27
Finalise mobile data collection system (phones, server, computer) | bar: August 24 to August 25; August 27
Identification and recruitment of interviewers | bar: August 24 to August 25
Sensibilization/Communication about the survey | bar: August 23 to August 25; August 28 to September 1
Survey training | bar: August 28 to September 1
Standardization test of the interviewers (Anthropometry) | bar: August 31
Pilot test | bar: September 1
Finalization of the fieldwork activities (planning, logistic) | bar: September 1
Data collection - Camp A | bar: September 3 to September 8
Data collection - Camp B | bar: September 17 to September 19; September 21 to September 22; September 24
Data collection - Out of Camp | bar: September 25 to September 29; October 1; October 3 to October 6; October 8
Data review and data analysis | bar: October 9 to October 15
Presentation of the main results to the MoH | bar: October 16
Departure of the UNHCR Consultant | bar: October 17
Drafting of final report | bar: October 18-28
Review of final report by the Technical Committee | bar: October 18-28
Presentation and dissemination of results and final report | bar: October 18-28
|  |  |  | Public Holidays | [6 empty] | Day Off

## FRENCH exemple
| Avril | [27 empty] | Mai | [30 empty] | Juin
| 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Finalisation du budget et du protocole d'enquête
Préparation du questionnaire, du guide de l'enquêteur et de tous les outils de formation et d'enquête
Arrivée du consultant HCR dans le pays
Validation de l'échantillonnage
Finalisation des outils de formation et d'enquête, et du questionnaire
Organisation de la formation des enquêteurs (logisitique, impression, etc.)
Finaliser l'installation du système de collecte des données mobile (téléphones, serveur, ordinateur)
Identification et recrutement des enquêteurs
Sensibilisation/Communication à propos de l'enquête
Formation des enquêteurs
Test de standardisation des enquêteurs
Voyage des équipes vers la zone des camps
Test pilote dans le camp A
Collecte des données - Camp A
Collecte des données - Camp B
Collecte des données - Camp C
Collecte des données - Camp D
Retour des équipes à la capitale
Vérification et analyse des données
Présentation des résulats préliminaires
Départ du consultant HCR
Rédaction du rapport final
Revue du rapport final par l'équipe technique
Présentation et dissémination des résultats et du rapport final
[5 empty] | Jours fériés | [6 empty] | Jours non-travaillés