## Financial Offer
ANNEX C: FINANCIAL OFFER FORM
SRFP/HCR/RCSEE/2026/008 ESTABLISHMENT OF A DATABASE AND SOFTWARE SOLUTION FOR RECORDING AND MONITORING THE INTEGRATION OF PERSONS GRANTED ASYLUM IN THE REPUBLIC OF SERBIA
No | Item Description | Period | Deliverable / Milestone | Total costs in RSD | Description of cost
1 | Definition of the system’s functional, technical requirements and hosting model | 1–15 September 2026 | Technical proposal in line with ToR, endorsed by the Commissariat for Refugees and Migration | 0
2 | Development of the software and system testing | 15 September – 15 November 2026 | Delivery of Database and Software Solution, endorsed by the Commissariat for Refugees and Migration | 0
3 | Training of employees, and transfer of ownership | 15 November – 31 December 2026 | Migration to State Data Center, Training and software ownership handover process completed, as certified by the Commissariat for Refugees and Migration. | 0
4 | Technical Support and warranty maintenance | 1 January – 31 December 2027 | Technical support and maintenance in line with offer. | 0
Total |  |  |  | 0
Name of the Company
Name of the Manager
Date and Signature/Stamp
Notes:
The above table will be the basis of Financial Evaluation of your offer by UNHCR: to be completed by the bidders
Please add as many lines as needed with the cost for a better understanding of the budget.